## Slide 1
Monitoring and Review
© 2002 IPC Certificate in Commissioning and Purchasing for Public Care.
All rights reserved.
Notes: By the end of this session, we are moving more specifically into the review quadrant of the commissioning cycle, considering how we monitor and performance manage our commissioned providers / services.
This is adding onto our discussions around outcome based commissioning, and we will start with exploring how we monitor services to ensure outcomes are achieved, as well as counting what is delivered.

## Slide 2: Why is monitoring and review important?
Why is monitoring important?
How can monitoring not be beneficial?
Notes: Two questions to prompt an initial discussion about peoples thoughts, reservations and experience of monitoring.
Do in plenary
OR
Do in pairs with one person answering each question
Some suggestions are on the following slide…

## Slide 3: Why is monitoring and review important?
Having good quality information and analysis to:
Judge efficiency and effectiveness
To provide challenge and look for continuous improvement
Making decisions about inefficient, ineffective and unsustainable services:
Supporting and challenging
Decommissioning and finding other provision
Notes: How can monitoring not be beneficial?
What you measure you concentrate on improving, which can generate actions that have nothing to do with improving quality. Perverse incentives.
Years ago the Audit Commission had an indicator around the number of people on trolleys in hospital corridors – one enterprising hospital moved people in beds out in the corridors, and those in trolleys in the wards to improve their performance…
Indicators are only indications of performance.
Burdensome on providers (and us potentially) – are we actual using what we are asking for, or just going through the motions?
Why is monitoring and review important?
Understanding the success of services is essential to inform and review commissioning decisions. Commissioners need good-quality information and analysis to help them judge the efficiency and effectiveness of services, and to justify changes to internal and external services and contracts in order to achieve a good standard of service delivery.
Measurements should be used to check that what we thought were the right ways to achieve some goal are actually delivering, and if not, to reconsider strategies and objectives. In the contract management process, we need all parties to actively measure and challenge each other against the promises and commitments made in the contract and to look for continuous improvement. Ideally, we want everything to go as planned without the need for extra measures and discussions or disputes for in that direction my increased costs and decreased output performance and overall unsatisfactory contract management.
Where performance management indicates that services are inefficient, ineffective or unsustainable, commissioners will either support and challenge that service to improve it, or, decommission it and find other provision to meet the identified needs.
We should never disappoint a partner and never be afraid to publicly celebrate successes. There's always a social side to business relationships. And we need to pay attention to these dimensions, alongside quantified performance indicators.
How can monitoring not be beneficial?
What you measure you concentrate on improving, which can generate actions that have nothing to do with improving quality. Perverse incentives.
Years ago the Audit Commission had an indicator around the number of people on trolleys in hospital corridors – one enterprising hospital moved people in beds out in the corridors, and those in trolleys in the wards to improve their performance…
Indicators are only indications of performance.

## Slide 4: Effective monitoring and review
Monitoring and Reporting
Evaluation and Review
Take Action
Performance Measures
Notes: [Note Animation. This slide aims to break down the stages of monitoring and review into measurement, monitoring and reporting, and evaluation. It emphasises the importance of taking action. Each click brings in different aspects, and the last few clicks animates take action]
The IPC performance monitoring and review model is a three stage approach – performance measurement, performance monitoring, and evaluation.
Performance Measurement is about defining measures (or indicators), which should be specified in specs/contracts. Remember that an objective is what you want to achieve and an indicator is what you need to count to know if that objective has been achieved. So, your measures (or indicators or KPIs) should relate back to the purpose/aims of the service.
'Monitoring' means regularly measuring what's going on with your service, your schemes or the effect of your activity.
Once the information has been captured it then needs to be analysed and acted upon to be of use. 'Evaluating' means drawing conclusions from the monitoring data on how well the service or schemes are performing or the effect of the activity.
Monitoring and evaluation are therefore two distinct activities within the review stage, monitoring being impartial and factual while evaluation tends to be more subjective and value laden. It is important therefore to set-up systems to evaluate the information collected and ensure that action is taken - taking action on the information is the most important thing.
Looking at each in turn… next: Measures

## Slide 5: Step 1: Agree what’s needed to demonstrate impact - ‘performance measures’ or ‘objectives’
Ordinary and unique lives for adults with a learning disability and/or autism: a six steps approach (2020) IPC
Advocacy services are readily available and able to work with everyone regardless of their communication needs
‘Service’ Objective
Support more people manage crisis when it happens and steadily support them to bring the situation back to one where their problems can be tackled over time
‘Strategic’ Objective
“get a paid job”
“managing my health better”
Individual wellbeing outcome
Notes: So in the paper we suggest that commissioners, preferably from health and the local authority and coproduced with people with lived experience to agree on what their model of care should look like
These potential outcomes / objectives and performance measures are considered at 3 different levels – the individual outcome, the service objective and the strategic / system level objective for the local area.

## Slide 6: Step 2: How will you know the service is having an impact?
What national measures do you have to collect or are set out?
Notes:   When identifying performance measures for outcomes, its also worth considering any national indicators you / providers have to collect or report on e.g.
  National Adult Social Care Outcomes Framework (ASCOF) and toolkit (ASCOT) social care- related quality of life in a number of domains e.g. control over daily life, personal safety, and dignity
  Public Health Outcomes Framework
  The NHS Outcomes Framework
  NHS friends and family test (FFT) introduced in 2013 and asks patients whether they would recommend hospital wards, A&E departments and maternity services to their friends and family if they needed similar care or treatment. The FFT became available in GP practices on December 1 2014 and then expanded to mental health services and community services on January 1 2015. Other services have been offerring the friends and family test from April 2015 such as NHS dental practices, ambulance services
  Patient Reported Outcome Measures (PROMs) assess the quality of care delivered to NHS patients from the patient perspective. http://www.hscic.gov.uk/proms
Beyond this you will want to define your own measures to demonstrate progress.

## Slide 7: Measures that you use
Where there are gaps in national information?
What local measures do you already use to fill these gaps, and what else might you want to collect?
  Does the performance indicator communicate the message clearly?
  Does the indicator say something important about the objective?
  Do you have quality data on a timely basis?
Do you have an overview of what is collected from providers by the CQC, Ofsted, ICBs and the local authority?
In the interests of efficiency, are you seeking to minimise duplication?
Notes: The following three criteria can be used to choose local indicators:
Does the indicator communicate well? The data must be common sense and compelling. The crime rate has communication power.
Does the indicator say something of central importance about the objective?
Is the data reliable and consistent? How much staff time is available to collect, analyse and present findings?

## Slide 8: Effective monitoring and review
Performance Measures
Monitoring and Reporting
Evaluation and Review
Take Action
Notes: We are moving onto stage 2 of this model
The IPC performance monitoring and review model is a three stage approach – performance measurement, performance monitoring, and evaluation.
Performance Measurement is about defining measures (or indicators), which should be specified in specs/contracts. Remember that an objective is what you want to achieve and an indicator is what you need to count to know if that objective has been achieved. So, your measures (or indicators or KPIs) should relate back to the purpose/aims of the service.
'Monitoring' means regularly measuring what's going on with your service, your schemes or the effect of your activity.
Once the information has been captured it then needs to be analysed and acted upon to be of use. 'Evaluating' means drawing conclusions from the monitoring data on how well the service or schemes are performing or the effect of the activity.

## Slide 9: Step 3: How do you measure or monitor the impact?
Service user/carer outcomes
Population outcomes
Social outcomes/Social Value
Economic outcomes
Efficiency outcomes
Legal compliance outcomes
Notes: As previously discussed, when thinking about impact and outcomes, there are a number of levels you might wish to consider and monitor to know that the service you have commissioned is making the intended difference.

## Slide 10: Measuring/monitoring for outcomes
Mark Friedman 2005
Notes: [From ‘Trying Hard is not Good Enough’ Mark]. Ask if people are familiar with this approach? If so, could get them to explain the basics…
Three simple performance measurement categories: How much did we do? How well did we do it? Is anyone better off?
Quantity of effort: How much service was provided? Quality of effort: How well was the service provided? For each activity in the upper left quadrant, there are one or more measures in the upper right quadrant that tell how well that particular activity is performed. Typically the number of service users and activities and measures such as turnover rate and unit cost. There are also activity-specific measures in this quadrant
Quantity of effect: How many service users are better off? Quality of effect: What percentage of service users are better off and how are they better off? The lower quadrant measures are for example the number and percentage of people who stopped using alcohol and drugs. These measures almost always have to do with one of four dimensions of better-offness: skills/knowledge, attitude/opinion, behaviour and circumstance.
The upper left quadrant is the least important quadrant. The lower right quadrant is the most important. i.e. these are the results or outcomes that we want to achieve. We have least control over the most important measures. It is harder to get data for the lower right hand quadrant, which is why people often focus on the top left quadrant
Service user satisfaction is one type of measure that applies to all services. “Did we treat you well?” “Did we help you with your problems?”
The key question to ask yourself when setting measures is ‘How can we measure if our patients/service users are better off?’
Although a model that has been around for a while, the theory behind it is still very much relevant and evident for public services. In fact, in 2022 the Northern Ireland Executive Office, drew upon the work of Mark Friedman, and developed an easy to use ‘report card’ template for public services to demonstrate the impact of a programme. The report cards are designed around the three questions asked here, and are the used on specific groups of customers rather than all of N Ireland.

## Slide 11: Measuring outcomes
Perception
Objective evidence
Interviews
Focus Groups
Questionnaires
Direct Observation
Document Analysis
Assessment
Notes: Measuring outcomes is generally harder than measuring other types of objectives. There are two main ways to do it:
Perceptions – this is the qualitative evidence. Its what people think has happened, their views and feelings. Predominantly the service users’ but could be others’ perception of the quality of the service, its effectiveness or its impact on them. These perceptions can be gained from postal surveys, by telephone, face to face during reviews or monitoring exercises, or by using more sophisticated tools such as Discovery Interviews or quality of life indicators.
Objective evidence – this is the quantitative evidence, specific criteria that demonstrate that there has been change for the individual. For example by direct observation, or document analysis or assessment by others such as support workers or GPs.
NB: relative value of these methods of collecting impact information is their effectiveness in changing organisational behaviour. Evidence shows that occasional third party questionnaires have little impact but using information from reviews systematically can be very effective.
There are various outcome measuring tools commonly used. Some tools consist of scale measure data which graphically displays progress on outcomes over time. Learning from practice has shown that without sufficient training and support for practitioners, tools which primarily focus on measures can close down the conversation, with the focus being on ticking the boxes. Other tools emphasize narrative data, with scale measures as a secondary component. More often, there is a tendency in support plans and reviews to collect both scale measures and narrative information about outcomes. The scale measure data tends to be high level, reporting on categories of outcomes such as ‘feeling safe and secure.’ The narrative identified the details of the outcome from the individual perspective. Learning from practice suggests that different styles of tool suit different individuals. Scale measures therefore can give a numerical rating for outcomes for the individual. By collating scale measure data, it is also possible to track outcomes for a given service or population. The narrative data gives more specific information about outcomes for individuals. By collating and analysing narrative data, through support plans and reviews, it is possible to get a better understanding of what works well and less well in achieving outcomes at aservice or local level.

## Slide 12: Individual outcomes
Anecdotes/quotes
Case studies
Self-reported change
Surveys (Before/After)
Comparison Groups
Random Control trials
Any others?
Dan Corry, Chief Executive of New Philanthropy Capital (NPC)
Notes: This lists some options available to public bodies to monitor outcomes at an individual level.
Self-reported change –examples of this approach will be covered on the next few slides
Comparison groups and RCTs are rarely used in public care – ethically this could feel dicey, as you are intentionally not providing support or an intervention to some people to see if the intervention makes a difference. Probably the most scientific, but a hard one to promote when we are in the business of helping people.

## Slide 13: Example – outcomes star
A tested and effective motivational tool, which services integrate into assessment and review
Record where client is and how they progress in up to 10 areas of their life
Scales are underpinned by a journey of change
Triangle Consulting Social Enterprise
Notes: In terms of self reported change, Here is one example.
The Outcome Star is a tested and effective motivational tool which services integrate into assessment and review to record where a client is and how they progress (outcomes) within up to 10 areas of their life. The Outcomes Star was originally developed by Triangle Consulting within the homelessness sector. There are different versions of the star including: mental health; homelessness; wellbeing; life star (LD); community; and a older person’s star.
All the versions of the star follow a similar pattern consisting of scales and a star chart.
The 10 scales are underpinned by a journey of change – an understanding of how people change and the various turning points and steps involved. This helps clients and worker understand where someone is in their own process at a given time, as a basis for developing a support plan. It also facilities the meaningful collation of outcomes data across a service and also across types of service and client group within the authority.
The Outcomes Star and supporting materials can be downloaded from www.outcomesstar.org.uk
An example of the outcome star is in your radar link.

## Slide 14: Case Study Example – Hertfordshire 6 Outcome Bees
Notes: Another example of a children’s self reported change scale / outcomes on children’s ambitions.
The Six Hertfordshire Outcome Bees are a set of key outcome areas/ domains for children, young people and their families. They were developed to align priorities and measure progress in meeting outcomes for all children at both an individual and strategic level in Hertfordshire.
The SEND Local Area inspection of Hertfordshire in 2016 identified a need for strategic alignment across programmes and services for children and young people with SEND. Herefordshire wanted to develop a set of shared multi-agency outcomes for all children, young people and families in Hertfordshire in order to improve outcomes and ensure coordination and consistency across services. They also wanted to change our focus from measuring what we did to measuring the impact of what we did.
The Outcomes Bees were formally launched across all agencies in Hertfordshire on 18th April 2018. These outcome bees were tested with children, young people and young adults, schools, parent carers and professional stakeholders

## Slide 15: Example - ReQoL
https://youtu.be/GwgS1QgfCgg
Notes: The Recovering Quality of Life Index (ReQOL) is a more recently introduced tool which was co-produced with service users and is focussed on recovery and wellbeing compared to other more clinical diagnostic tools, so is more person-centered and holistic.
Recovering Quality of Life (ReQoL) has been developed to assess the quality of life of people with different mental health conditions. ReQoL is a brief outcome measure focusing on the process of recovery for users of mental health services.
There are two versions, with 10 or 20 questions, and they can be completed by the service user and reviewed as part of support conversations.
It was developed by a team at The University of Sheffield in 2016 to capture the concerns of service users on their quality of life. This work was commissioned and funded by the Department of Health Policy Research Programme in England for use in the NHS.
It covers seven themes: activity, hope, belonging and relationships, self-perception, well-being, autonomy, and physical health.
The benefits of this outcome measurement tool:
Consistent with the themes of recovery
Constructed using considerable inputs from service users and clinicians
Acceptable to service users and clinicians
Short and simple to use
Suitable for a range of mental health conditions from common mental health disorders to more severe ones
ReQoL has been developed using a robust methodology and is psychometrically sound
Preference weights will be available for the ReQoL to generate quality adjusted life years.
Free for the NHS and for publicly funded research
There have been some research regarding the validity of the tool showing some promising results in terms of the consistency and reliability of the tool for mental health outcomes.
The video link (do not show unless you have lots of time), helps give more information on this toolkit. A summary document is also available in your pack.

## Slide 16: Service / Support intervention-based outcomes
Client Groups | The Service will contribute to individuals | Impact Statements
1. Children & Young People (Families / Child Health & Disability) | Help to deal with past trauma and progression into functioning adults Staying in their own home where appropriate Engaged with the local community Accessing & Maintaining education/ employment Having a Healthy & Positive Lifestyle Engaged in social activities Socialising, forming relationships, friendships & connections Successful transition into adulthood | Young People are being supported to remain at home – not admitted to care Progress for family in promoting stability & reducing stresses on the family supporting them to live independently Community connections
2. Children & Young People with a Learning Disability | Positively managing challenging behaviour Living as independently as they can Living within their communities Engaging in education / training / employment Forging networks, friendships & meaningful relationships | As above – maybe less of a reduction in care package but sustained over a longer period of time Progress for the individual Individual able to live independently with support & progress in to adulthood supporting them to live independently Community connections
Notes: This is an example of potential outcome monitoring more on a service level rather than individual
As well as providers of care and support demonstrating how they are meeting the individual needs and wishes / outcomes of the people in receipt of their care - this approach allows commissioners to monitor if the provider as a whole is achieving strategic outcomes for the organization – such as keeping young people safe and out of hospital, supporting children to remain at home and not in care etc. So you might be looking to set a target on the % of young people who are meeting these impact statements, or asking for an upwards or downwards trend for example for the people the provider is supporting / working with

## Slide 17: Service / Support intervention-based outcomes
Client Groups | The Service will contribute to individuals | Impact Statements
3. Young People and Children with mental health | Having self-awareness and supported by network of people using recovery model or therapeutic interventions Being safe and living in secure accommodation and strong support networks Living more independently Individuals supported in their recovery to live meaningful lives with or without symptoms of their conditions Being a positively engaged citizen Promoting and connecting families, friends and communities to reduce social isolation | Individual having reduced hospital admissions or need to seek help. Individual having reduced admissions to hospital Individual having reduced formal admissions to hospital Individual helped with recovery Individual helped to develop the resources and capabilities needed to live independent lives. Supporting children, young people and families to live independently
4. Young People and Children with a physical and sensory impairment | Helped to live with condition in own home Being a positively engaged citizen Promotion of self-care / management Promoting and connecting families, friends and communities to reduce social isolation | Individual is helped in a way that might reduce need for formal care Supporting children, young people and families to live independently
Notes: This is an example of potential outcome monitoring more on a service level rather than individual
As well as providers of care and support demonstrating how they are meeting the individual needs and wishes / outcomes of the people in receipt of their care - this approach allows commissioners to monitor if the provider as a whole is achieving strategic outcomes for the organization – such as keeping young people safe and out of hospital, supporting children to remain at home and not in care etc.

## Slide 18: Population based outcomes
Quality-Adjusted Life Year (QALY)
“A measure of the state of health of a person or group in which the benefits, in terms of length of life, are adjusted to reflect the quality of life. One quality-adjusted life year (QALY) is equal to 1 year of life in perfect health.
QALYs are calculated by estimating the years of life remaining for a patient following a particular treatment or intervention and weighting each year with a quality-of-life score (on a 0 to 1 scale). It is often measured in terms of the person’s ability to carry out the activities of daily life, and freedom from pain and mental disturbance.”
This is how NICE decide what medical treatments to approve - £30K per life-year!
Can we find a social care equivalent?
Notes: Finally, some organisations might wish to think about population or ‘place’ level outcomes – indicators that demonstrate as a place or system people are generally healthy, safe and happy.
The QALY I an example of this type of indicator – used to demonstrate as a whole if people in a local area (or in receipt of a particular intervention) has a better quality of life
But the wider you take your measurements the more challenging attrition becomes.

## Slide 19: Selecting the right measures
Seek input and buy-in from a wide range of stakeholders
Acknowledge individual/local/national priorities
Set realistic targets
Select a mix of outcomes, outputs and process measures
Prioritise the most important measures
Be creative and flexible
Consider how the data can be collected and analysed
Keep it simple
SCIE, 2019
Notes: This is SCIE (Social Care Institute of Excellence)’s advice for selecting the right monitoring measures. It does acknowledged a wholly outcomes based monitoring arrangement might be preferable – particularly if we want to demonstrate value for money and quality assurance and compliance – therefore a balance between monitoring outcomes, outputs and processes is recommended.

## Slide 20
Scenario-based exercise

## Slide 21: Stage 3
You are reviewing a set of outcomes and measures relating to homeless people in the area:
Consider the proposed measures and monitoring arrangements: how realistic are they? Any changes or additions?
Revisit your original outcomes:
  Are they the right ones?
  Would you revise any of them?
Notes: Returning the homeless exercise from earlier (or previous day)
Flip chart returned to the original group (if delivering in person)
You now have, in very rough form, an outline outcome based specification for this service you want to commission.
The second bullet point asks the group to think about how they would turn this into reality.

## Slide 22: Effective monitoring and review
Performance Measures
Monitoring and Reporting
Evaluation and Review
Take Action
Notes: Finally, we will look at stage 3 and importantly taking action!
The IPC performance monitoring and review model is a three stage approach – performance measurement, performance monitoring, and evaluation.
Performance Measurement is about defining measures (or indicators), which should be specified in specs/contracts. Remember that an objective is what you want to achieve and an indicator is what you need to count to know if that objective has been achieved. So, your measures (or indicators or KPIs) should relate back to the purpose/aims of the service.
'Monitoring' means regularly measuring what's going on with your service, your schemes or the effect of your activity.
Once the information has been captured it then needs to be analysed and acted upon to be of use. 'Evaluating' means drawing conclusions from the monitoring data on how well the service or schemes are performing or the effect of the activity.
Monitoring and evaluation are therefore two distinct activities within the review stage, monitoring being impartial and factual while evaluation tends to be more subjective and value laden. It is important therefore to set-up systems to evaluate the information collected and ensure that action is taken - taking action on the information is the most important thing.
Looking at each in turn… next measures

## Slide 23: Step 4: Evaluation and action
Remember – monitoring performance alerts you to the fact that a problem exists, not why it exists.
Explain rather than describe problems, including how they will be addressed.
In order to address poor performance you need to analyse reasons behind it and take action.
Mark Friedman 2005
Notes: Importance of actually doing something with the information you collect – analysing it and understanding the story it is telling you about whether a service is doing what we hoped it would.
Explain rather than describe problems. If performance is not on target reports should explain why and what will be done to rectify the problem – many areas use an Outcome Based Accountability report card to present results (more information on OBA is in your radar link)
Create a culture in which success is applauded but in which the approach is to minimise the likelihood of failure, if it does occur steps should be taken to ensure that the lessons are learned to prevent repetition in the future. Can you foster a double loop learning approach in which the root causes of problems are analysed and dealt with rather than simply taking short term corrective action?
Have an expectation of how managers will respond if poor performance is highlighted – e.g., a clear, transparent policy which outlines your response.
Give providers time to analyse and develop a corrective action plan (CAP) before information is published. Interpret information thoughtfully.

## Slide 24: Improving performance through effective contracting monitoring
Proportional investment in monitoring with levels of action based on risk.
Rely on providers’ QA systems i.e. use self assessment and providers’ information plus random samples/unannounced visits to ensure honesty and accuracy.
Agree protocols on intervention with underperforming providers.
Set-up systems to ensure action is taken.
Publicise the results.
Notes: What can be monitored and what is monitored are often very separate as resources invested in monitoring are usually only a very small proportion of the total value of contracts. To ensure effective monitoring:
Relate the investment in monitoring to the risk. Levels of action based on risk e.g. named contract manager for contracts over a certain amount, major contracts have a timetable etc. Risk could be based on:
  Value of contract
  Number of patients/service users
  Other factors such as political or strategic importance or high profile
Use self assessment and providers PIs plus random sample to ensure honesty and accuracy. Have a structure to unannounced visits and consider using local user groups for them or other doing mystery shopping. Balance between time and how directly contract monitoring staff are involved with the provision of the service and service users
Ensure that all providers know what will happen if they under perform.
Do what you threaten!
Publicise performance against standards to all stakeholders - make sure patients/users and carers are informed.

## Slide 25: Managing poor performance
Aspect | Developmental Approach
Basic principles | Mistakes happen. Everyone should have the chance to learn from them and change. Support may be needed to prevent recurrence.
In practice | Purchaser and provider agree on what has gone wrong and why. Develop a corrective action plan (CAP), which may include additional monitoring and support.
Benefits | Reflects mutual dependence and partnership. Can enable ‘business as usual’ whilst some matters are resolved.
Risks | No immediate consequences for provider – long term deterrent? CAP may not resolve the problem; termination may only be delayed
Gosling
Notes: Thinking specifically about contract management…
If performance is poor, what do you do? Two main schools of thought on this – developmental versus punitive approach, but remember that taking action (whichever approach) is the key thing:
Developmental approach
Basic Principles - Mistakes happen. Everyone should have the chance to learn from them and to change in order to prevent recurrence. Support may be needed to achieve this.
In Practice - Purchaser and provider agree on what has gone wrong and why. Develop a corrective action plan (CAP), which may include additional monitoring and/or support for the provider. The contract makes explicit this way of resolving performance problems, and allows eventual termination if satisfactory performance is not re-established.
Benefits - Reflects mutual dependence and partnership. Can enable ‘business as usual’ while some matters are resolved. The provider is likely to be positively motivated.
Risks Provider may think they can ‘get away with it’ as there are no immediate consequences. CAP may not resolve the problem; termination may only be delayed not prevented.
Taken from the DH eBook article by Doug Gosling on Contract Monitoring.

## Slide 26: Managing poor performance
Aspect | Punitive Approach
Basic principles | Performance can never be below required standards. Financial or other punishments will prevent recurrence of problems. The provider must resolve their problems alone.
In practice | The threat or implementation of fine or restriction of new business. Suspension from accredited list. The contract must contain explicit powers.
Benefits | Clear relationship between performance and payments. Shows purchaser’s serious intent from the outset.
Risks | Judgements open to legal challenge. Purchaser may be drawn into terminating contract sooner than they would want.
Gosling
Notes: Punitive approach
Basic Principles - Performance can never be below required standards. Financial or other punishments will prevent recurrence of problems. The provider must resolve their problems alone.
In Practice - The threat or implementation of the reduction of payment or restricting new business. Suspension from accredited list. The contract must contain explicit powers for the purchaser to reduce or withhold payments or restrict new business in specified circumstances.
Benefits - Clear relationship between performance and payments. Shows purchaser’s serious intent from the outset.
Risks - Purchaser drawn into terminating the contract sooner than they would want. Judgements to justify decisions to reduce payments or reduce business open to legal challenge. Contract must enable purchaser to take punitive actions.

## Slide 27: What determines your approach?
The seriousness of the matter
The risk(s) involved
Has the contract been breached?
The relationship with the provider
The providers response to poor performance
Notes: What determines your approach to managing poor performance when monitoring contracts i.e. whether to be developmental or punitive?
The seriousness of the matter
Where the delivery of the service and/or the quality of care being provided is in question, this will always be more serious than administrative or financial problems. Seriousness will often be linked to risk.
The risk(s) involved
This will usually be focused on service users, though risks to staff are equally relevant. Another key area of risk is to consider whether the service as a whole is at risk. If closure or withdrawal of registration are possible consequences of the poor performance there are potentially very significant risks for all service users who will need alternative care. Generally, the higher the risks, the more immediate and substantial the response must be.
Has the contract been breached?
Has the provider failed to comply fully with the requirements of the contract? When considering poor performance, it is vital to refer back to the contract, to focus on exactly how the provider has not complied with the contract.
The relationship with the provider
The realities of limited contract monitoring resources and variable provider performance require us to embrace proportionality, i.e. the response to a high quality provider with very few examples of poor performance would be very different to the response to a poor quality provider with a long history of things going wrong.
The provider’s view and response to the poor performance
When asked about poor performance, a provider may openly confirm where things have gone wrong and show they have or are planning to prevent them recurring. At the other extreme, the provider may either deny there is a problem or, as more frequently happens, provide a series of excuses.

## Slide 28: Getting it right
Be seen to be consistent, equitable and objective
Work with providers to set up and manage the process
Meet with providers or review monitoring information from providers regularly
Review what matters and demonstrate that data is used
Notes: Be seen to be consistent, equitable and objective - equity for all organisations (including internal as well as external providers) is key here. It is a level playing field in your local area? If not, what do you think are the reasons for this and/or is that appropriate?
Work with providers to set up and manage the process.
Monitor what matters and what is contractually required. Link into existing reporting processes and don’t ask for too much information, crucially, demonstrate to providers that the data they provide is used.
Therefore, develop local indicators but do not overburden providers with too many targets.

## Slide 29: Managing poor performance
What arrangements do you have put in place to be able to respond robustly to poor contractual performance?
Notes: Group Discussion – ask this question to the room – share what works well and any challenges experienced
No need to spend too long on this, as leads into the next breakout exercise.

## Slide 30: Your current organisational approach
Consider your local approach to monitoring and review…
Are you looking at the right measures?
What are your monitoring arrangements?
How do they relate to your contract management processes?
What action, of any, takes place?
Identify 2 key areas for improvement
Measures
Performance monitoring
Contract management
Improvement
Notes: Breakout group discussion
Handout in radar link Contract Management Principles. Good practice contract management principles from the Crown Commercial Service. Not necessarily all relevant to local government, but a useful set of principles to help you reflect on your contract management activities, including monitoring.

## Slide 31: Contact us
https://ipc.brookes.ac.uk
ipc_courses@brookes.ac.uk
01865 790312
institute-of-public-care-brookes